## Sheet1
Bug Id | Bug description | Business Impact | Status | Assignee
IAL-1 | Candidate landing page does not shows all the questions that are assign to the candidate | 1. Candidate will not able to see the questions on their landing page 2. This will leads to loss of infformation to a candidate | Code Fix and Unit Testing Completed | Sudha
IAL-2

## Sheet2
Bug Status
Issue Identified
Root Cause Analysis Complted
Code Fix and Unit Testing Completed
Code reivew Completed
Test Deployed
Testing Completed
UAT Deployed
UAT Completed
Production Deployed